## Gantt Chart Template
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Idea del Proyecto
1.1 | Tipo de Juego | Alejandro | 2022-09-26 | 2022-09-26 | 1 | 100% | bar: WEEK 1 M; WEEK 2 M to WEEK 2 T
2 | Programación del Juego
| Clicks por Tile | Adrià | 9/26/22 | 9/26/22 | 1 | 100% | bar: WEEK 1 M; WEEK 2 M to WEEK 2 T
| Tilemap | Alejandro | 9/26/22 | 9/27/22 | 2 | 100% | bar: WEEK 1 M to WEEK 1 T; WEEK 2 M to WEEK 2 T
| Sprites(GUI, Player,Enemigos) | Alejandro | 9/27/22 | 9/27/22 | 1 | 100% | bar: WEEK 1 T; WEEK 2 M to WEEK 2 T
| GUI | Alex | 9/27/22 | 2022-10-09 | 14 | 100% | bar: WEEK 1 T to WEEK 3 W
| GameOver | Alex | 2022-10-01 | 2022-10-03 | 2 | 100% | bar: WEEK 2 M to WEEK 2 W
| Vida | Adrià | 10/1/222 | 10/1/222 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
| Moneda | Alex | 2022-10-01 | 2022-10-02 | 2 | 100% | bar: WEEK 2 M to WEEK 2 T
| Player | Adrià | 2022-10-01 | 2022-10-06 | 6 | 100% | bar: WEEK 2 M to WEEK 3 M
| Pathfinding Player | Alex | 10/6/202 | 10/8/202 | 2 | 100% | bar: WEEK 2 M to WEEK 2 T; WEEK 3 M to WEEK 3 T
| Enemigos | Alejandro | 10/6/202 | 10/09/202 | 3 | 100% | bar: WEEK 2 M to WEEK 2 T; WEEK 3 M to WEEK 3 W
| Pathfinding Enemigo | Alejandro | 10/8/202 | 10/9/202 | 2 | 100% | bar: WEEK 2 M to WEEK 2 T; WEEK 3 T to WEEK 3 W
| Animaciones | Alejandro | 10/10/202 | 10/10/202 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T; WEEK 3 R
| Rankings | Alex | 10/1o/202 | 10/1o/202 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T; WEEK 3 R
| Colorear Tiles Pasables | Alex | 10/10/202 | 10/11/202 | 2 | 100% | bar: WEEK 2 M to WEEK 2 T; WEEK 3 R to WEEK 3 F
| Juntar Escenas | Adrià | 10/12/202 | 10/12/202 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T; WEEK 4 M